## PV
Proyecto
Earned Value Analysis Report
Prepared By:
Date:
[42]
For Period:
Summary:
El periodo indica semana terminada
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1 | actividad 1 | 1000000 | 1000000 | [13 empty] | ← Enter or edit values in the light-blue cells.
1.2 | actividad 2 | 70000 | 20000 | 50000
1.3 | actividad 3 | 80000 |  | 30000 | 10000 | 40000
2.1 | actividad 4 | 100000 |  | 50000 | 30000 | 10000 | 10000
2.2 | actividad 5 | 60000 |  |  |  | 20000 | 20000 | 20000
← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
| Total Budgeted Cost | 1310000 | 1020000 | 130000 | 40000 | 70000 | 30000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Planned Value (PV) | 1020000 | 1150000 | 1190000 | 1260000 | 1290000 | 1310000 | 1310000 | 1310000 | 1310000 | 1310000 | 1310000 | 1310000 | 1310000 | Línea azul en el gráfico
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 302500 | 440000 | 687500 | 1072500 | 1127500 | 1265000 | 1265000 | 1265000 | 1265000 | 1265000 | 1265000 | 1265000 | 1265000 | Línea roja en el gráfico
|  | Cumulative Earned Value (EV) | 1017500 | 1078000 | 1144000 | 1192000 | 1192000 | 1204000 | 1204000 | 1204000 | 1204000 | 1204000 | 1204000 | 1204000 | 1204000 | Línea verde en el gráfico
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 715000 | 638000 | 456500 | 119500 | 64500 | -61000 | -61000 | -61000 | -61000 | -61000 | -61000 | -61000 | -61000 | Lo que deberia haber costado el trabajo realizado en el periodo según las estimaciones, contra el gasto de lo que realmente se trabajo
|  | Schedule Variance (SV = EV - PV) | -2500 | -72000 | -46000 | -68000 | -98000 | -106000 | -106000 | -106000 | -106000 | -106000 | -106000 | -106000 | -106000 | La cantidad de plata gastada según las estimaciones, contra lo que teniamos planificado gastar en un periodo
|  | Cost Performance Index (CPI = EV/AC) | 3.3636 | 2.45 | 1.664 | 1.1114 | 1.0572 | 0.95178 | 0.95178 | 0.95178 | 0.95178 | 0.95178 | 0.95178 | 0.95178 | 0.95178 | Relación proporcional entre el gasto estimado de lo que se trabajo en el periodo y lo que realmente costo en base a lo trabajado
|  | Schedule Performance Index (SPI = EV/PV) | 0.99755 | 0.93739 | 0.96134 | 0.94603 | 0.92403 | 0.91908 | 0.91908 | 0.91908 | 0.91908 | 0.91908 | 0.91908 | 0.91908 | 0.91908 | Relación proporcional entre el gasto estimado de lo que se trabajo en el periodo y lo que se tenia estimado trabajar
|  | Estimated Cost at Completion (EAC) | 389459.4595 | 534693.8776 | 787259.6154 | 1178670.302 | 1239114.9329 | 1376370.4319 | 1376370.4319 | 1376370.4319 | 1376370.4319 | 1376370.4319 | 1376370.4319 | 1376370.4319 | 1376370.4319 | (No entra) Estimación del costo total del proyecto al finalizar (El BAC (Budget at Completion, por sus siglas en inglés) se refiere al presupuesto total aprobado para completar un proyecto)
|  | Semana | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | CSI | 3.3554 | 2.2966 | 1.5997 | 1.0514 | 0.97689 | 0.87476 | 0.87476 | 0.87476 | 0.87476 | 0.87476 | 0.87476 | 0.87476 | 0.87476 | Indicador cuantitativo que define que tan probable esta el proyecto para recuperarse, mientras más alejado del 1 es menor probable
Fecha oficial inicio de proyectos
Fecha presentación de proyectos terminados
Total semanas |  |  | 13
Valor UF (Horas hombre) |  |  | 27500
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## Control del proyecto
Control del proyecto
Porcentaje trabajado por período
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13
1.1 | actividad 1 | 1000000 | 100% | [12 empty] | 100%
1.2 | actividad 2 | 70000 | 25% | 75% | [11 empty] | 100%
1.3 | actividad 3 | 80000 |  | 10% | 20% | 10% | 60% | [8 empty] | 100%
2.1 | actividad 4 | 100000 |  |  | 50% | 50% | [9 empty] | 100%
2.2 | actividad 5 | 60000 |  |  |  | 80% | 0% | 20% | [7 empty] | 100%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
- | - | 0 | [13 empty] | 0%
Insert new rows above this one
|  | Cumulative EV | 1017500 | 1078000 | 1144000 | 1250000 | 1298000 | 1310000 | 1310000 | 1310000 | 1310000 | 1310000 | 1310000 | 1310000 | 1310000

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV) (Curva Verde)
WBS | Task Name | Total | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13
1.1 | actividad 1 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | actividad 2 | 70000 | 17500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | actividad 3 | 24000 | 0 | 8000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | actividad 4 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | actividad 5 | 60000 | 0 | 0 | 0 | 48000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insert new rows above this one
|  | Total Earn Value | 1017500 | 60500 | 66000 | 48000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Earn Value (EV) | 1017500 | 1078000 | 1144000 | 1192000 | 1192000 | 1204000 | 1204000 | 1204000 | 1204000 | 1204000 | 1204000 | 1204000 | 1204000

## Horas
Horas trabajadas
Horas trabajadas por período
Total
WBS | Task Name | Total | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13
1.1 | actividad 1 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | actividad 2 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | actividad 3 | 13 | 0 | 3 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | actividad 4 | 11 | 0 | 0 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | actividad 5 | 9 | 0 | 0 | 0 | 4 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insert new rows above this one
|  | Total Horas | 11 | 5 | 9 | 14 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total horas Acumuladas | 11 | 16 | 25 | 39 | 41 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed (Curva Roja)
WBS | Task Name | Total | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13
1.1 | actividad 1 | 247500 | 247500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | actividad 2 | 110000 | 55000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | actividad 3 | 357500 | 0 | 82500 | 110000 | 110000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | actividad 4 | 302500 | 0 | 0 | 137500 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | actividad 5 | 247500 | 0 | 0 | 0 | 110000 | 0 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insert new rows above this one
|  | Total Actual Cost | 302500 | 137500 | 247500 | 385000 | 55000 | 137500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 302500 | 440000 | 687500 | 1072500 | 1127500 | 1265000 | 1265000 | 1265000 | 1265000 | 1265000 | 1265000 | 1265000 | 1265000